## Intro
Scrum Excel sheet
Your Product Name : | My Product
Welcome to the Touilleur Express Excel Sheet for Scrum
Product Backlog
The Product Backlog is the list of functionalities desired for the product. The Product Owner
updates the list of items using user stories. During Sprint Planning Meeting, you must fix
the order of desired items once for all.
Report to a Sprint sheet the selection of items that the team will produce during the sprint
Note on Usage :
As a product owner, enter all items in the Product Backlog in the blue area.
As a Scrum Master, conducts a Sprint Planning Meeting, compute the estimated amount of
scrum units required to complete a task. Split in small task if necessary in the Sprint sheet.
Once the amount of scrum units is choosen by the team, update the "calculs" sheet to
compute the curve of remaining scrum units per days
Nicolas Martignole
Certified Scrum Master
Blog le Touilleur Express
http://touilleur-express.fr
Published under a Commons Creatives License
See http://fr.creativecommons.org/ and http://creativecommons.org/
Le Touilleur Express Excel Sheet for Scrum by Nicolas Martignole http://touilleur-express.fr is licensed under a Creative Commons Attribution 2.0 France License.
Based on a work at touilleur-express.fr.

## Product Backlog
Product Backlog
Titre | En tant que … | Je peux … | Domaine | Priorité | Difficulté | Plannifié dans le sprint
| Visiteur | Accéder à la page d’accueil | Home
| Visiteur | Créer un compte | Compte
| Visiteur | me connecter | Compte
| Visiteur | demander à récupérer mon mot de passe | Compte
| Visiteur ou Utilisateur | Rechercher un trajet | Trajet – passager
| Visiteur ou Utilisateur | Saisir un trajet | Trajet – conducteur
| Visiteur | Voir le profil public d’un autre utilisateur | Profils
| Utilisateur | Modifier mon compte | Compte
| Utilisateur | Supprimer mon compte | Compte
| Utilisateur | Définir mon ou mes véhicules | Compte
| Utilisateur | Voir le profil complet d’un autre utilisateur | Profils
| Utilisateur | Réserver un trajet | Trajet – passager
| Utilisateur | Annuler une réservation | Trajet – passager
| Utilisateur | Valider un trajet | Trajet – conducteur
| Utilisateur | Annuler un trajet | Trajet – conducteur
| Utilisateur | Payer mon trajet | Trajet – passager
| Utilisateur | Voir les réservations passager sur mon trajet | Trajet – conducteur
| Utilisateur | Accepter ou refuser les réservations sur mon trajet | Trajet – conducteur
| Utilisateur | Voir les trajets en cours | Liste trajets
| Utilisateur | Voir les trajets effectués | Liste trajets
| Utilisateur | Evaluer un utilisateur avec qui j’ai partagé un trajet | Profils
| Administrateur | me connecter au back-office | Admin
| Administrateur | gérer les utilisateurs | Admin
| Administrateur | Définir les prix de base par catégorie de véhicules | Admin

## Sprint 1
| Sprint 1 | Start date | 2008-10-21
| My Product | End date (included) | 2008-11-04
|  | Initial Scrum Effort | 0
|  | Sprint objectives | To set-up a login page and be able to build and test.
user story | Task | Value/Importance | Initial Estimate | 2008-07-21 | 2008-07-22 | 2008-07-23 | 2008-07-24 | 2008-07-25 | 2008-07-28 | 2008-07-29 | 2008-07-30 | 2008-07-31 | 2008-08-01
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <= Remaining Scrum Units
|  |  | Forecast | 8 | 7.1111 | 6.2222 | 5.3333 | 4.4444 | 3.5556 | 2.6667 | 1.7778 | 0.88889 | 0 | 0
Note on B6: Reuters Financial Software: Insert here a quick and short descriptive name for the story. Clear enough so that developers understand what we are talking about and clear enough to distinguish it from other stories. Usually 2 to 10 words
Note on C6: Reuters Financial Software: This is the product owner's importance rating for this story. The higher is the value, the more important is this story. There is no max value, and we tend to avoid to use "priority 1" cause if you later decide that something else is even more important, do you think you would put "priority 0" or "priority -1" ? ?
Note on D6: Reuters Financial Software: This is the team's initial assessment of how much work is needed to implement this story compared to other stories. The unit is story points and usually corresponds roughly to "ideal man days". The importance is to undertand that this is just a relative value that will be accurate if you compute-it with the Team's velocity. If a team velocity is 3 units / days then you can quickly figure-out when the req might be ready. This part (all green items) must be filled by KARMA developers only. Not by the product owner
Note on D16: nicolas.martignole: Initial total of Scrum units
Note on E17: nicolas.martignole: Edit this cell formula and make a link to the calculs Sheet so that the graph is generated automatically

## Sprint 2
| Sprint 2 | Start date | 2008-10-21
| My Product | End date (included) | 2008-11-04
|  | Initial Scrum Effort | 10
|  | Sprint objectives | To set-up a login page and be able to build and test.
ID | Short name | Value/Importance | Initial Estimate | 2008-07-21 | 2008-07-22 | 2008-07-23 | 2008-07-24 | 2008-07-25 | 2008-07-28 | 2008-07-29 | 2008-07-30 | 2008-07-31 | 2008-08-01
| Sample user story |  | 10 | 2008-07-21: 0
|  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <= Remaining Scrum Units
|  |  | Forecast | 8 | 7.1111 | 6.2222 | 5.3333 | 4.4444 | 3.5556 | 2.6667 | 1.7778 | 0.88889 | 0 | 0
Note on B6: Reuters Financial Software: Insert here a quick and short descriptive name for the story. Clear enough so that developers understand what we are talking about and clear enough to distinguish it from other stories. Usually 2 to 10 words
Note on C6: Reuters Financial Software: This is the product owner's importance rating for this story. The higher is the value, the more important is this story. There is no max value, and we tend to avoid to use "priority 1" cause if you later decide that something else is even more important, do you think you would put "priority 0" or "priority -1" ? ?
Note on D6: Reuters Financial Software: This is the team's initial assessment of how much work is needed to implement this story compared to other stories. The unit is story points and usually corresponds roughly to "ideal man days". The importance is to undertand that this is just a relative value that will be accurate if you compute-it with the Team's velocity. If a team velocity is 3 units / days then you can quickly figure-out when the req might be ready. This part (all green items) must be filled by KARMA developers only. Not by the product owner
Note on D17: nicolas.martignole: Initial total of Scrum units
Note on E18: nicolas.martignole: Edit this cell formula and make a link to the calculs Sheet so that the graph is generated automatically

## system sheet
Computation of remaining scrum units
|  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
Total scrum units estimated |  | 8 | 8
| Restant fin | 0 | 0 | 0 | 0 | 0 | 0
Do not edit table content | Days: | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Known X
| Sprint 1 | 8 | 7.1111 | 6.2222 | 5.3333 | 4.4444 | 3.5556 | 2.6667 | 1.7778 | 0.88889 | 0 | 0
| Sprint 2 | 8 | 7.1111 | 6.2222 | 5.3333 | 4.4444 | 3.5556 | 2.6667 | 1.7778 | 0.88889 | 0 | 9
| Sprint 3 | [10 empty] | 1
Sprint 4
Sprint 5
Sprint 6
Description :
This table computes the theorical amount of remaining work per days. Value in blue bold are linked to "Sprint 01" and "Sprint 02" sheets.
Note on C6: 513334: Enter here the amount of scrum units the team decided to produce in the sprint